## Dashboard
ClearSight Dental — Pilot Compliance Baseline
HIPAA Pilot Controls • Phase 1.5 Hosted Beta • v1.0 • April 2026
Status summary |  | Legend
Controls total | 25 | Complete
Controls complete | 0 | In progress
Controls in progress | 0 | Not started
Controls not started | 25 | N/A
% complete | 0%
Pilot-gating controls outstanding | 14
How to use this workbook
• The Controls sheet is the source of truth. Update Status column G as work progresses.
• Controls marked "Blocker" must be Complete before the pilot URL is shared with Dr. Basher.
• The Evidence sheet tracks where each control’s supporting artifact lives (runbook section, screenshot, policy doc).
• The Audit Calendar sheet is the action list for the next 180 days.
• This workbook is refreshed at every monthly compliance review; the owner is Dale (founder) until a Head of Security is hired.

## Controls
Control ID | Framework | Requirement | Description | Owner | Priority | Status | Target date | Evidence ref | Notes
CS-A-01 | HIPAA §164.308(a)(1) | Security Management Process | Document and maintain a written HIPAA security risk analysis covering the hosted pilot scope. | Dale | Blocker | Not started | 2026-04-30 | EV-01 | Use NIST SP 800-30 template; scope is hosted-backend + frontend + Postgres.
CS-A-02 | HIPAA §164.308(a)(2) | Assigned Security Responsibility | Designate a Security Official accountable for HIPAA compliance. | Dale | Blocker | Not started | 2026-04-20 | EV-02 | Dale serves as interim Security Official until hire. Document in company policy.
CS-A-03 | HIPAA §164.308(a)(3) | Workforce Security | Role-based access policy; authorize workforce members before granting PHI access. | Dale | Blocker | Not started | 2026-04-25 | EV-03 | Only Dale + 1 engineer with PHI access at pilot launch.
CS-A-04 | HIPAA §164.308(a)(5) | Security Awareness & Training | HIPAA security awareness training for all workforce with PHI access, completed before launch. | Dale | Blocker | Not started | 2026-04-25 | EV-04 | Use free HHS training modules or a paid provider (e.g., Accountable, Compliancy Group).
CS-A-05 | HIPAA §164.308(a)(6) | Security Incident Procedures | Written incident response plan including breach classification and notification workflow. | Dale | Blocker | Not started | 2026-04-28 | EV-05 | Runbook §Escalation covers the operational steps; formal policy still needed.
CS-A-06 | HIPAA §164.308(a)(7) | Contingency Plan | Data backup plan, disaster recovery plan, emergency mode operation plan. | Dale | High | Not started | 2026-05-15 | EV-06 | Neon Postgres has point-in-time recovery; document RPO/RTO targets (<24h/<4h).
CS-A-07 | HIPAA §164.308(a)(8) | Evaluation | Periodic technical and non-technical evaluation against HIPAA standards. | Dale | Medium | Not started | 2026-07-01 | EV-07 | Quarterly cadence; first review 90 days after pilot launch.
CS-A-08 | HIPAA §164.308(b) | Business Associate Contracts | Signed BAAs with all subprocessors that touch PHI (Vercel, Fly.io, Neon, Resend, HF CDN). | Dale | Blocker | Not started | 2026-04-20 | EV-08 | Vercel Pro, Fly.io, Neon offer BAAs on request; confirm Resend HIPAA tier.
CS-P-01 | HIPAA §164.310(a) | Facility Access Controls | Physical access to systems processing PHI is restricted; inherited from cloud providers. | Dale | Medium | Not started | 2026-04-28 | EV-09 | Document reliance on AWS/GCP physical controls (via Fly.io and Neon hosting providers).
CS-P-02 | HIPAA §164.310(c) | Workstation Security | Workforce workstations with access to PHI are secured: FileVault, auto-lock, screen timeout. | Dale | High | Not started | 2026-04-25 | EV-10 | FileVault already enabled on Dale laptop; verify + document.
CS-P-03 | HIPAA §164.310(d) | Device and Media Controls | Procedures for disposal and re-use of media containing ePHI. | Dale | Medium | Not started | 2026-05-15 | EV-11 | Low exposure at pilot scale; document anyway for audit readiness.
CS-T-01 | HIPAA §164.312(a)(1) | Access Control — Unique User ID | Unique user identification for each workforce member and each practice user. | Engineering | Blocker | Not started | 2026-04-30 | EV-12 | Implemented via Postgres users table + magic-link auth; one row per user.
CS-T-02 | HIPAA §164.312(a)(2)(iii) | Automatic Logoff | Sessions expire after inactivity. | Engineering | High | Not started | 2026-04-30 | EV-13 | 15-minute idle timeout default; refresh with magic-link re-auth.
CS-T-03 | HIPAA §164.312(a)(2)(iv) | Encryption and Decryption (at rest) | AES-256 encryption at rest for all PHI stores. | Engineering | Blocker | Not started | 2026-04-30 | EV-14 | Neon Postgres encrypts at rest by default; Fly.io volumes encrypted; Vercel KV encrypted.
CS-T-04 | HIPAA §164.312(b) | Audit Controls | Hardware, software, and/or procedural mechanisms that record and examine activity in systems containing ePHI. | Engineering | Blocker | Not started | 2026-04-30 | EV-15 | audit_log table wired into every inference call; 6-year retention.
CS-T-05 | HIPAA §164.312(c)(1) | Integrity Controls | Mechanisms to ensure PHI is not improperly altered or destroyed. | Engineering | High | Not started | 2026-05-15 | EV-16 | Postgres append-only audit_log; SHA-256 on every image on ingest.
CS-T-06 | HIPAA §164.312(d) | Person or Entity Authentication | Procedures to verify that a person or entity seeking access is the one claimed. | Engineering | Blocker | Not started | 2026-04-30 | EV-17 | Magic-link auth with Resend; allowlist of authorized emails.
CS-T-07 | HIPAA §164.312(e)(1) | Transmission Security (in transit) | TLS 1.2+ for all PHI in transit, including between Vercel and Fly.io backend. | Engineering | Blocker | Not started | 2026-04-25 | EV-18 | Vercel enforces TLS 1.3; Fly.io enforces TLS 1.3; verify with SSL Labs scan.
CS-B-01 | HIPAA §164.404-408 | Breach Notification | Written breach notification procedure aligned to BAA §3(3)–(4) and HIPAA Breach Notification Rule. | Dale | Blocker | Not started | 2026-04-28 | EV-19 | Policy + template notification letters; cyber-liability carrier gets first call.
CS-O-01 | HIPAA §164.314 | Organizational Requirements | BAA in place before any PHI leaves the practice. Policies and procedures documented. | Dale | Blocker | Not started | 2026-04-20 | EV-20 | BAA v1.0 drafted; needs counsel review and countersignature.
CS-O-02 | Internal | Cyber-liability insurance | Cyber-liability policy bound at $5M/$5M per Clinical Pilot Agreement §12. | Dale | Blocker | Not started | 2026-04-30 | EV-21 | Quote from Coalition, At-Bay, or Cowbell; confirm HIPAA coverage explicit.
CS-O-03 | Internal | Acceptable Use Policy (internal) | Workforce AUP covering BYOD, password hygiene, and PHI handling. | Dale | Medium | Not started | 2026-05-15 | EV-22 | One-page policy; Dale signs first, future hires sign on Day 1.
CS-S-01 | State (Governing Law) | State medical-records law compliance | Confirm state-level patient records requirements for the governing-law state in CPA §13. | Counsel | High | Not started | 2026-05-01 | EV-23 | Most states track HIPAA; CA, TX, NY have additional state rules (CMIA, HB 300, SHIELD).
CS-F-01 | SOC 2 Type I | SOC 2 Type I readiness assessment | Engage auditor for SOC 2 Type I readiness assessment within 12 months. | Dale | Low | Not started | 2026-12-31 | EV-24 | Prerequisite for DSO contracts; Drata/Vanta/Secureframe as automation partner.
CS-F-02 | SOC 2 Type II | SOC 2 Type II audit | Complete SOC 2 Type II audit (12-month observation window) within 18 months. | Dale | Low | Not started | 2027-10-31 | EV-25 | Enterprise/DSO gating milestone; see Hosted Service Addendum §15.4.

## Evidence
Evidence ID | Control ref | Type | Location | Collected by | Date collected | Next refresh | Notes
EV-01 | CS-A-01 | Risk analysis document | /OpenRestaurant/compliance/hipaa-risk-analysis.docx | Dale |  | 2027-04-01 | Annual refresh.
EV-02 | CS-A-02 | Appointment memo | /OpenRestaurant/compliance/security-official-appointment.docx | Dale |  | On change | Re-execute on any change of officer.
EV-03 | CS-A-03 | Access roster | Controls sheet + Postgres users table | Dale |  | Monthly | Reconcile monthly with Postgres.
EV-04 | CS-A-04 | Training certificates | /OpenRestaurant/compliance/training/ | Dale |  | Annually | One PDF per workforce member.
EV-05 | CS-A-05 | Incident response plan | /OpenRestaurant/compliance/irp.docx | Dale |  | 2027-04-01 | Annual tabletop exercise; document results.
EV-06 | CS-A-06 | Contingency plan + backup test report | /OpenRestaurant/compliance/contingency-plan.docx | Dale |  | Semi-annual | Neon PITR test every 6 months.
EV-07 | CS-A-07 | Quarterly evaluation report | /OpenRestaurant/compliance/evaluations/ | Dale |  | Quarterly | First report due 90 days after launch.
EV-08 | CS-A-08 | Countersigned BAAs | /OpenRestaurant/compliance/baas/ | Dale |  | On renewal | One file per subprocessor.
EV-09 | CS-P-01 | Facility controls documentation | /OpenRestaurant/compliance/facility-controls.md | Dale |  | 2027-04-01 | Inherited control; document provider references.
EV-10 | CS-P-02 | Workstation security attestation | /OpenRestaurant/compliance/workstation-attestation.docx | Dale |  | Annually | Signed attestation per workforce member.
EV-11 | CS-P-03 | Media disposal log | /OpenRestaurant/compliance/media-disposal.xlsx | Dale |  | On event | Log each disposal event.
EV-12 | CS-T-01 | Auth config screenshot + schema | backend/app/schema.sql + screenshot | Engineering |  | Annually | Commit schema to git; screenshot during audit prep.
EV-13 | CS-T-02 | Session timeout config | frontend/auth config | Engineering |  | Annually | Code reference + operational test.
EV-14 | CS-T-03 | Encryption-at-rest attestation | Neon + Fly.io BAAs + screenshots | Engineering |  | Annually | Provider-issued attestation.
EV-15 | CS-T-04 | Audit log schema + sample query | backend/app/schema.sql + sample SELECT output | Engineering |  | Quarterly | Retention = 2190 days (6 years).
EV-16 | CS-T-05 | Integrity control code + tests | backend/app/audit.py + test suite | Engineering |  | Annually | SHA-256 of every ingested image.
EV-17 | CS-T-06 | Auth flow documentation | docs/auth.md + runbook Step 7 | Engineering |  | Annually | Magic-link flow diagram.
EV-18 | CS-T-07 | SSL Labs scan report | screenshot + URL snapshot | Engineering |  | Quarterly | Target A+ rating.
EV-19 | CS-B-01 | Breach notification policy + templates | /OpenRestaurant/compliance/breach-notification.docx | Dale |  | 2027-04-01 | Template letters for individuals, Secretary, media.
EV-20 | CS-O-01 | Countersigned pilot BAA | /OpenRestaurant/compliance/baas/dia-basher-dds.pdf | Dale |  | On renewal | File before first pilot sign-in.
EV-21 | CS-O-02 | Cyber-liability certificate of insurance | /OpenRestaurant/compliance/coi-cyber.pdf | Dale |  | Annually | Confirm HIPAA coverage explicit in declarations.
EV-22 | CS-O-03 | Acceptable Use Policy (signed) | /OpenRestaurant/compliance/aup.docx | Dale |  | On hire + annually | One signed copy per workforce member.
EV-23 | CS-S-01 | Counsel memo on state requirements | /OpenRestaurant/compliance/state-law-memo.pdf | Counsel |  | On state change | Re-run when adding a new state to the pilot.
EV-24 | CS-F-01 | SOC 2 Type I readiness report | /OpenRestaurant/compliance/soc2/readiness.pdf | Dale |  | Once | Engagement letter from chosen auditor.
EV-25 | CS-F-02 | SOC 2 Type II audit report | /OpenRestaurant/compliance/soc2/type2-report.pdf | Dale |  | Annually | Keep latest 3 years on file.

## Audit Calendar
Date | Activity | Related controls | Owner | Status | Notes
2026-04-20 | Counsel sign-off on BAA v1.0 and Clinical Pilot Agreement v1.0 | CS-A-08, CS-O-01 | Counsel | Not started | Hard blocker for pilot launch.
2026-04-20 | Appoint Security Official (Dale, interim) | CS-A-02 | Dale | Not started | Written appointment memo.
2026-04-22 | Bind cyber-liability policy ($5M/$5M) | CS-O-02 | Dale | Not started | Quote + bind; file COI.
2026-04-25 | Complete HIPAA security awareness training (Dale + Eng) | CS-A-04 | Dale | Not started | Certificate of completion.
2026-04-25 | SSL Labs scan of Vercel + Fly.io endpoints | CS-T-07 | Engineering | Not started | Must pass A rating before pilot open.
2026-04-28 | Finalize incident response + breach notification policy | CS-A-05, CS-B-01 | Dale | Not started | Templates ready to send.
2026-04-30 | Complete technical safeguards (auth, encryption, audit log) | CS-T-01..07 | Engineering | Not started | Per runbook Steps 5–8.
2026-04-30 | Countersign BAAs with Vercel Pro, Fly.io, Neon, Resend | CS-A-08 | Dale | Not started | Request during account setup.
2026-05-01 | Send pilot docs + URL to Dr. Basher | All Blockers | Dale | Not started | Gate on every Blocker row = Complete.
2026-05-15 | Complete Contingency Plan + first backup restoration test | CS-A-06 | Engineering | Not started | Document RPO/RTO actuals.
2026-05-15 | Publish internal Acceptable Use Policy | CS-O-03 | Dale | Not started | One-page; signed by all workforce.
2026-06-01 | 30-day pilot checkpoint with Dr. Basher | All | Dale | Not started | Walk through audit log with him.
2026-07-01 | First quarterly evaluation (CS-A-07) | CS-A-07 | Dale | Not started | Document findings + remediation.
2026-07-30 | 90-day Pilot Term end — convert or close out | All | Dale | Not started | Either sign production agreement or purge PHI per BAA §9(3).
2026-10-01 | SOC 2 Type I readiness engagement kickoff | CS-F-01 | Dale | Not started | Select Drata/Vanta/Secureframe.
2026-12-31 | SOC 2 Type I report issued | CS-F-01 | Dale | Not started | Share with DSO prospects in Q1 2027.
2027-04-01 | Annual risk analysis refresh | CS-A-01 | Dale | Not started | Redo using prior year as baseline.
2027-10-31 | SOC 2 Type II report issued | CS-F-02 | Dale | Not started | 12-month observation window closes Oct 2027.

## Gap Analysis
Framework | Requirement area | Current state | Target state | Gap | Priority | Est. effort
HIPAA | Administrative safeguards | None formally documented | Risk analysis + Security Official + workforce training | All administrative docs need to be created | Blocker | 2 weeks
HIPAA | Physical safeguards | Inherited from cloud providers; FileVault enabled | Documented inheritance + workstation attestations | Paper trail only | High | 3 days
HIPAA | Technical safeguards | Prototype has no auth, no audit log, localhost only | Magic-link auth + Postgres audit log + TLS 1.3 + tenant isolation | Build and deploy per runbook Steps 5–8 | Blocker | 1 week
HIPAA | Breach notification | No policy, no templates | Policy + template letters aligned to BAA §3(3)–(4) | Document creation | Blocker | 3 days
HIPAA | Organizational (BAAs + insurance) | Draft BAA; no insurance bound | Countersigned BAAs with subprocessors + $5M cyber policy | Legal + procurement | Blocker | 1 week
SOC 2 | Type I readiness | No controls mapped | Full control-to-criteria mapping via Drata/Vanta | Engage auditor | Low | 3 months
SOC 2 | Type II audit | Not in scope for pilot | 12-month observation + audit | Type I must complete first | Low | 18 months
State law | Governing-law state | TBD | Counsel memo confirming state-specific requirements | Counsel engagement | High | 1 week